## IP Address Plan
MCCCD AA140 — Device IP Address Plan (Main Conference Room)
Proposal 10297 / PO DSTOF-100135103 ¦ In-code IPs = values configured in SIMPL# Pro backend + CH5 panel ¦ Generated 2026-06-05
# | Device / Role | Model | Qty | Subsystem | IPID | In-Code IP (intended) | Assigned IP (field) | Status / Conflict | Notes
1. Control System
1 | Control processor | RMC4 | 1 | Control | host | 192.168.2.191 |  | OK | deploy.py=.1.191 vs NVX-Routing-Lessons=.2.198 — pick one
2 | Tabletop touchpanel | TS-1070-B-S | 1 | Control | 0x03 | 192.168.2.80 |  | OK | Drifted .2.53 > .1.175 > .2.80 (package.json deploy:tabletop)
3 | Wall touchpanel | TSW-1070-B-S | 1 | Control | 0x04 | 192.168.2.78 |  | OK | Historically .2.123 (package.json deploy:wall)
4 | Room scheduling panel | TSS-1070-B-S | 1 | Control | - | (none) |  | NEEDS IP | Standalone scheduler; not in code
2. AV-over-IP — DM NVX (IPID-bound, each needs an AV-VLAN IP)
5 | Encoder — Room PC (src 1) | DM-NVX-E30 | 1 | NVX | 0x11 | mcast 239.8.0.0 |  | NEEDS IP
6 | Encoder — Ext/Laptop PC (src 2) | DM-NVX-E30 | 1 | NVX | 0x12 | mcast 239.8.0.4 |  | NEEDS IP
7 | Encoder — AirMedia (src 3) | DM-NVX-E30 | 1 | NVX | 0x13 | mcast 239.8.0.8 |  | NEEDS IP
8 | Encoder — HDMI+USB-C (src 4) | DM-NVX-384 | 1 | NVX | 0x14 | mcast 239.8.0.12 |  | Needs IP | In code as src4 but NOT on BOM (3x E30 only) — confirm exists/OFE
9 | Decoder — Display 1 | DM-NVX-D30 | 1 | NVX | 0x21 |  |  | NEEDS IP
10 | Decoder — Display 2 | DM-NVX-D30 | 1 | NVX | 0x22 |  |  | NEEDS IP
11 | Decoder — Display 3 | DM-NVX-D30 | 1 | NVX | 0x23 |  |  | NEEDS IP
12 | Decoder — Display 4 (podium confidence) | DM-NVX-D30 | 1 | NVX | 0x24 |  |  | NEEDS IP
13 | Decoder — Display 5 (signage, outside room) | DM-NVX-D30 | 1 | NVX | 0x25 |  |  | NEEDS IP | Independently routable signage feed
3. Audio — Shure
14 | Audio conferencing DSP | P300-IMX | 1 | Audio | - | 192.168.2.151 |  | OK | Consistent in ShureP300Service + DeviceConfigStore
15 | Ceiling array mic A | MXA920W-S | 1 | Audio | - | 192.168.2.181 |  | OK
16 | Ceiling array mic B | MXA920W-S | 1 | Audio | - | 192.168.2.182 |  | OK
4. Cameras — 1Beyond (VISCA TCP 5500 + RTSP 554)
17 | PTZ camera — Front (20x) | IV-CAM-I20-B | 1 | Camera | - | 192.168.2.172 |  | OK | CameraService=.2.172 / cameras.ts=.1.172 / memory=.1.174
18 | PTZ camera — Back (12x) | IV-CAM-I12-B | 1 | Camera | - | 192.168.2.173 |  | OK | CameraService=.2.173 / cameras.ts=.1.172 / memory=.1.173
5. Wireless Presentation — AirMedia
19 | AirMedia receiver | AM-3200-WF | 1 | Presentation | - | 192.168.2.177 |  | OK | Consistent in AirMediaService + DeviceConfigStore
- | Connect endpoint (table) | AM-TX3-200 | 1 | Presentation | - | (pairs to rx) |  | NO IP | Pairs to AM-3200; no static IP normally
- | Connect adaptor | AM-TX3-100 | 1 | Presentation | - | (pairs to rx) |  | NO IP | Pairs to AM-3200; no static IP normally
6. USB Routing
20 | BYOD USB matrix switcher | USB-SW-400 | 1 | USB | 0x31 | (none) |  | NEEDS IP | Controlled IP device (UsbSwitchService); hosts Room PC/AirMedia/Laptop
7. Network Infrastructure
21 | Managed AV PoE switch | Netgear M4250 (GSM4230P) | 1 | Network | - | (none) |  | NEEDS IP | Management IP; not in code
8. OFE — network-controlled (IPs in code)
22 | Projector 1 | OFE (Sony VPL) | 1 | Display | - | 192.168.2.161 |  | OK | SonyVplService=.2.161 vs DeviceConfigStore sony-1=.2.191
23 | Projector 2 | OFE (Sony VPL) | 1 | Display | - | 192.168.2.162 |  | OK | SonyVplService=.2.162 vs DeviceConfigStore sony-2=.2.192
24 | Newline interactive display | OFE | 1 | Display | - | 192.168.2.171 |  | OK | NewlineService=.2.171 vs DeviceConfigStore newline=.2.195

## Satellite Rooms (ref)
Satellite Rooms — separate Archon project 'MCCCD Conference Room' (2 identical rooms)
Device / Role | Model | Qty per room | Needs IP? | Notes
Control processor | RMC4 | 1 | Yes
Tabletop touchpanel | TS-770-B-S | 1 | Yes
AirMedia receiver | AM-3100-WF | 1 | Yes
Videobar 70 (MTR) | UC-SB2-CAM-A-T | 1 | Yes | Camera+mic+speakers+MTR PC
Connect endpoint (table) | AM-TX3-200 | 1 | No | Pairs to AM-3100
Display | OFE | 1 | Maybe | Direct connection; IP only if network-controlled